## ProjectTeam
Name | GitHub Alias | Function
Stefan Iseli | isels1 | Srum Master & Developer
Tim Dorner | dornt1 | Developer
Christine Noser | nosec1 | Developer
Fabian Zwahlen | zwahf1 | Developer
Lukas Hügi | hugil1 | Developer

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original in h | Effort Plan Updated in h | Effort Actual in h | Status
1 | Authentication | A Health Visitor wants to login into the application |  | 12 |  | 16.5
2 | Show Calendar | A Health Visitor wants to see all his appointements in a calendar view |  | 28 |  | 34
3 | Add new Appointment | A Health Visitor wants to add a new Appointmen |  | 12 |  | 16
4 | Show Patients | A Health Visitor wants to see all his patients in one view |  | 36 |  | 36
5 | Show Patient Detail | A Health Visitor wants to see the details of a patient
6 | Show Patient Treatment | A Health Visitor wants to see the details of a treatment

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original in h | Effort Plan Updated in h | Effort Actual in h | Status
1.5 | 1 | Implement all "base" Interfaces | Implement all the base Interfaces for the base Classes of our Class Diagram | Interfaces | nosec1 | isels1 | hight | 4 |  | 7 | done
1.6 | 1 | Implement all "base" Classes | Implement all the base Classes (Objetcs) of our Class Diagram | BusinesClasses | hugil1 | isels1 | hight | 6 |  | 9 | done
1.7 | 1 | Implement Health Visitors Dummy Objects | Implement Dummy Health Visitors | DummyData | isels1 | dornt1 | hight | 2 |  | 0.5 | done
2.2 | 1 | Implement Calendar View | Implement the Vaadin View for the Calendar Weekly View | Views | dornt1 | isels1 | hight | 6 | 8 | 15 | done
2.3 | 1 | Implement Calendar Dummy Objects | Implement Dummy Calendars | DummyData | isels1 | dornt1 | hight | 2 |  | 0.5 | done
2.5 | 1 | Implement Appointment Dummy Objects | Implement Dummy Appointments for the Calendars | DummyData | isels1 | dornt1 | hight | 2 |  | 0.5 | done
2.6 | 1 | Implement UI Controller for Calendar View | Implement the UI Cotroller for the Calendar View | Controller | zwahf1 | isels1 | hight | 6 |  | 4 | done
2.7 | 2 | Implement the weekly view | Implementing the weekly Calendar view according the planned state event diagramm | Views | dornt1 | isels1 | hight | 6 |  | 4 | done
2.8 | 2 | Implement the monthly view | Implementing the monthly Calendar view according the planned state event diagramm | Views | dornt1 | isels1 | hight | 6 |  | 4 | in progress
3.1 | 2 | Implement new Appointment Pop-Up View | Implementing the Pop-Up View for the new Appointment with the nessecairy fields | Views | zwahf1 | dornt1 | hight | 6 |  | 8 | done
3.2 | 2 | Implement new Appointment Pop-Up UIController | Implementing the functionality for the new Appointment function | Controller | zwahf1 | dornt1 | hight | 6 |  | 8 | open
4.1 | 2 | Implement Dummy Patients | Implementing some dummy Patients for the Patient List view | DummyData | nosec1 | isels1 | hight | 6 |  | 2 | in progress
4.2 | 2 | Plan State-Event-Diagram for Pat.Status | Plan the state event pattern for the Patient State | Planing | isels1 | hugil1 | hight | 4 |  | 2 | donw
4.3 | 2 | Implement Patient List View | Implement the Pattient List View after hugil1 has designed it and made a prototype | Views | nosec1 | isels1 | hight | 6 |  | 12 | done
4.4 | 2 | Implement Patient retrieve functionality UIController | Implementing the retrieve Patients functioanality for the Patient List view | Controller | isels1 | zwahf1 | hight | 2 |  | 2 | done
4.5 | 2 | Implement new Patient view | Implementing the popup with the necessairy fields for new Patients functionality | Views | hugil1/dornt1 | zwahf1 | hight | 6 |  | 10 | done
4.6 | 2 | Implement new Patient logic | Implementing the functions (logic) for the new Patient functionsality | Controller | isels1 | isels1 | hight | 4 |  | 4 | done
4.7 | 2 | Create GUI Planning Patient List | Creating and Planing the GUI for the Patient List View and make a little prototype | Views | hugil1 | isels1 | medium | 4 |  | 2 | done
4.8 | 2 | Create GUI Planning new Patient | Creating and Planing the GUI for the new Patient View with a little Prototype. IMPORTANT: DO SHOW ALL NECESSAIRY FIELDS!! | Views | hugil1 | isels1 | medium | 4 |  | 2 | done
2.8 | 2 | Fix the monthly view | Implementing the monthly Calendar view according the planned state event diagramm | Views | dornt1 | isels1 | hight | 2 |  |  | open
3.2 | 2 | Fix new Appointment Pop-Up UIController | Implementing the functionality for the new Appointment function | Controller | zwahf1 | dornt1 | hight | 2 |  |  | open
5.1 | 3 | Implement Patent Detail View | implementing the detail view for the patient | Views | zwahf1 |  |  | 2 |  |  | Waiting
5.2 | 3 | Implement Treatment Overview Tab | implementing the detailview for the treatment overview | Views | zwahf1 |  |  | 2 |  |  | Waiting
5.3 | 3 | Implement Appointment Tab | implementing the view of the appointment tab | Views | zwahf1 |  |  | 2 |  |  | Waiting
5.4 | 3 | Implement Info Tab Detail | implementing the view of the detail tab | Views | zwahf1 |  |  | 2 |  |  | Waiting
5.5 | 3 | Implementing Classes for Treatment | implementing the class whit all mehtos in the model | Model | isels1 |  |  | 4 |  |  | Waiting
|  | Implementing Controller for Patient detail Tretment | implementing the controller layer for the treatent class | Model | isels1 |  |  | 2
1.1 | 3 | Design Database | A tinty design for the needed database. | DB | hugil1 | isels1 |  | 4 |  |  | Waiting
1.2 | 3 | Implement Database | Implement/Create the Database | DB | hugil1 | isels1 |  | 6 |  |  | Waiting
1.3 | 3 | Implementing Database Connection Layer |  | Persistence | dornt1 | isels1 |  | 6 |  |  | Waiting
1.4 | 3 | Insert Dummy Data in Database | Fill the Database whit dummydata for presenting the project | DB | dornt1 |  |  | 2
1.4 | 3 | Implement Authentication View | Implement the Vaadin View for the Login |  | nosec1 |  |  | 4 |  |  | Waiting
1.5 | 3 | Implement Authentication Cotroller | Implement the Controller for the Login |  | nosec1 |  |  | 4 |  |  | Waiting
1.6 | 3 | Implement Authentication in Database | implementing the authentication layer for the login view |  | nosec1 |  |  | 2 |  |  | Waiting
1.7 | 3 | Edit code Design for login | edit the code desing for the login screen. Login screen ist the first view when starting the app |  | isels1 |  |  | 4 |  |  | Waiting
50

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180