## ProjectTeam
Name | GitHub Alias | Function
Stefan Iseli | isels1 | Srum Master & Developer
Tim Dorner | dornt1 | Developer
Christine Noser | nosec1 | Developer
Fabian Zwahlen | zwahf1 | Developer
Lukas Hügi | hugil1 | Developer

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original in h | Effort Plan Updated in h | Effort Actual in h | Status
1 | Authentication | A Health Visitor wants to login into the application |  | 24
2 | Show Calendar | A Health Visitor wants to see all his appointements in a calendar view |  | 34
3 | Add new Appointment | A Health Visitor wants to add a new Appointmen
4 | Show Patients | A Health Visitor wants to see all his patients in one view
5 | Show Patient Detail | A Health Visitor wants to see the details of a patient
6 | Show Patient Treatment | A Health Visitor wants to see the details of a treatment

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original in h | Effort Plan Updated in h | Effort Actual in h | Status
1.1 |  | Design Database | A tinty design for the needed database. |  | hugil1 |  | low | 2 |  |  | open
1.2 |  | Implement Database | Implement/Create the Database |  | hugil1 |  | low | 4 |  |  | open
1.3 |  | Implement Authentication View | Implement the Vaadin View for the Login |  | zwahf1 |  | medium | 4 |  |  | open
1.4 |  | Implement Authentication Cotroller | Implement the Controller for the Login |  | zwahf1 |  | medium | 2 |  |  | open
1.5 | 1 | Implement all "base" Interfaces | Implement all the base Interfaces for the base Classes of our Class Diagram | Interfaces | nosec1 | isels1 | hight | 4 |  | 7 | in progress
1.6 | 1 | Implement all "base" Classes | Implement all the base Classes (Objetcs) of our Class Diagram | BusinesClasses | hugil1 | isels1 | hight | 6 |  | 9 | in progress
1.7 | 1 | Implement Health Visitors Dummy Objects | Implement Dummy Health Visitors | DummyData | isels1 | dornt1 | hight | 2 |  | 0.5 | done
2.2 | 1 | Implement Calendar View | Implement the Vaadin View for the Calendar Weekly View | Views | dornt1 | isels1 | hight | 6 | 8 | 15 | in progress
2.3 | 1 | Implement Calendar Dummy Objects | Implement Dummy Calendars | DummyData | isels1 | dornt1 | hight | 2 |  | 0.5 | done
2.5 | 1 | Implement Appointment Dummy Objects | Implement Dummy Appointments for the Calendars | DummyData | isels1 | dornt1 | hight | 2 |  | 0.5 | done
2.6 | 1 | Implement UI Controller for Calendar View | Implement the UI Cotroller for the Calendar View | Controller | zwahf1 | isels1 | hight | 6 |  | 4 | done
2.7 |  | Implement the weekly view | Implementing the weekly Calendar view according the planned state event diagramm | Views | dornt1 | isels1 | hight | 6
2.8 |  | Implement the monthly view | Implementing the monthly Calendar view according the planned state event diagramm | Views | dornt1 | isels1 | hight | 6
3.1 |  | Implement new Appointment Pop-Up View |  | Views | zwahf1 | dornt1 | hight | 6
3.2 |  | Implement new Appointment Pop-Up UIController |  | Controller | zwahf1 | dornt1 | hight | 6
4.1 |  | Implement Dummy Patients |  | DummyData | nosec1 | isels1 | hight | 6
4.2 |  | Plan State-Event-Diagram for Pat.Status |  | Planing | isels1 | hugil1 | hight | 4
4.3 |  | Implement Patient List View |  | Views | nosec1 | isels1 | hight | 6
4.4 |  | Implement Patient retrieve functionality UIController |  | Views | isels1 | zwahf1 | hight | 2
4.5 |  | Implement new Patient view |  | Controller | isels1 | zwahf1 | hight | 6
4.6 |  | Implement new Patient logic |  | Controller | hugil1 | isels1 | hight | 4
4.7 |  | Create GUI Planning Patient List |  | Views | hugil1 | isels1 | medium | 4
4.8 |  | Create GUI Planning new Patient |  | Views | hugil1 | isels1 | medium | 4
5.1 |  | Implement Info Tab Detail
5.2 |  | Implement Treatment Overview Tab
5.3 |  | Implement Appointment Tab
5.4 |  | Implement Patent Detail View
60

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180